## Implementasi
TABEL IMPLEMENTASI MMOGLE (ACCELERATED + spesifically aligned with Ford Motor Co.USA requirements)
"A" level targeted compliance and within 3 months of development
No. | Phase | Minggu | Fokus | Aktivitas Detail (Praktis) | Requirement OEM (simulation: Ford Motor Company USA Perspective) | Output | Parallel / Overlap
1 | Project Kick-Off & Governance | W1 | Alignment & target | - Pem,bentukan task force (SCM, PPIC, WH, IT, and other relevant divisions, on demand) - Define KPI (OTIF, inventory, traceability) - Setup special room untuk monitoring perkembangan proyek berbasis: harian - 2 hari - Training Event Awareness Theme: MMOGLE with "A" level requirement setting (lihat: Lampiran Syllabus/Rundown Training) | - KPI harus align global OEM - Accountability yang jelas | Project charter | Paralel assessment
2 | MMOGLE Assessment & Gap | W1–2 | Current state vs Level A | - Audit internal (planning, WH, logistics) - Data collection (line stop, OTIF) - Scoring awal | - OEM audit focus: data vs actual consistency | Gap matrix | Overlap design
3 | Solution Design (OEM Driven) | W2–3 | Future state >> yang relevan dengan requirement MMOGLE & OEM (simulation) | - Design inventory control - Design feeding system - Design export flow - Risk mapping supply chain (new requirements) | - Harus support: • No disruption • High predictability | Roadmap implementasi | Paralel quick wins prep
4 | Improvement & Stabilization | W3–6 | Eliminasi masalah kritikal dari hasil Assessment & GAP Analysis | - Cycle count harian (ABC) - FIFO visual control - Layout zoning RM/WIP/FG - Fix receiving & issuing error | - Inventory accuracy ≥98% - No hidden stock | Stabilitas awal | Paralel system build
5 | Inventory Accuracy & Traceability | W3–8 | Data reliability | - Barcode / batch tracking - Stock reconciliation harian - Batch mapping RM → FG tyre | - Full traceability:RM → tyre → shipment - Recall capability <48 jam | Accuracy ≥98% | Overlap WMS
6 | Line Feeding System (Zero Stop) | W4–8 | Production continuity | - Milk run system - Supermarket line - Min-max stock - FIFO feeding | - Zero line stop akibat material - JIT readiness | Line stabil | Paralel warehouse
7 | Focus: Warehouse aligning with MMOGLE with "A" level requirement & (simulation of) Ford USA requirements | W4–9 | Flow & efficiency | - Layout flow-based - Fixed bin location - Fast/slow moving separation - FIFO enforcement | - No mixing batch - Visual control audit-ready | WH optimal | Overlap WMS
8 | Focus: Planning & MRP improvement & Stabilization | W5–9 | Demand-supply sync | - Validasi BOM - Setup MPS & MRP - Forecast review - Frozen schedule | - Schedule stability wajib - No last-minute change | Planning stabil | Paralel supplier
9 | Supplier Integration & Control | W5–10 | Inbound reliability | - Delivery agreement - ASN (advance shipment notification) implementation - Supplier OTD monitoring - Dual & Multiple sourcing strategy | - Supplier OTD ≥ 95–98% - ASN visibility wajib | Supplier reliable | Overlap planning
10 | WMS / ERP Integration | W6–10 | Digital control | - Real-time inventory - Batch tracking system - System-directed picking - Integrasi produksi | - Real-time data mandatory - No manual override | System reliable | Paralel semua
11 | Export Logistics Optimization | W6–10 | OTIF global delivery | - Container planning weekly - Loading standard - Export doc checklist - Sync dengan produksi | - OTIF (On Time-In Full) ≥ 98% - No shipment delay - Accurate doc | Export stabil | Overlap planning
12 | KPI Dashboard & Control Tower | W7–11 | Monitoring real-time | - Dashboard: • OTIF • Inventory • Line stop - Daily war room - Escalation cepat | - Visibility end-to-end- Decision real-time | Control system | Paralel full
13 | SOP & Standardization | W8–11 | Sustain system | - SOP planning, WH, feeding, export - Training operator - Visual SOP di shopfloor - 2 hari - Training Event Theme: Conducting Audit: MMOGLE with "A" level requirement setting (lihat: Lampiran Syllabus/Rundown Training) | - Standardisasi global - Audit compliance | SOP siap audit | Overlap audit prep
14 | Audit Simulation (OEM Style) | W10–11 | Audit readiness | - Mock audit (data vs actual) - Traceability test - FIFO audit | - OEM audit: • Random trace test • System check | Pre-score Level A | Paralel closing
15 | Final Gap Closing | W11–12 | Final improvement | - Closing gap audit - Fine tuning KPI - Stabilkan proses | - Semua KPI harus stabil (bukan trial) | Level A ready | Intensif
16 | Final Review & Sustainability | W12 | Maintain Level A | - Management review - CI system (Kaizen) - Audit readiness | - Continuous improvement mandatory | Sustain system | -

## syllabus training
HARI 1 — FUNDAMENTAL + OEM EXPECTATION AWARENESS
Waktu | Modul | Materi Utama | Integrasi Perspektif OEM (Ford) | Metode | Output
08.30–09.00 | Opening & Pre-Test | - Intro MMOGLE- Pre-test | - OEM mindset: supplier harus reliable | Quiz | Baseline peserta
09.00–10.15 | Intro MMOGLE + OEM Requirement | - MMOGLE overview sederhana- Level A concept | - Supplier harus: • OTIF ≥98% • No disruption • Full visibility | Visual + analogi | Paham ekspektasi OEM
10.15–10.30 | Break
10.30–11.45 | Supply Chain Tyre End-to-End | - Flow tyre manufacturing- Critical material (rubber, chemical) | - OEM demand: • Stable supply • No batch defect • Consistent lead time | Flow diagram + studi kasus | Paham flow + risk
11.45–12.45 | Inventory Management (OEM View) | - FIFO - Inventory accuracy | - Ford requirement: • Inventory accuracy ≥ 98% • No hidden stock • Traceable batch | Simulasi | Paham kontrol inventory
12.45–13.45 | Lunch
13.45–15.00 | Warehouse Management (Audit View) | - Layout & zoning - Storage discipline | - OEM audit focus: • FIFO compliance • No mixing batch • Visual control jelas | Visual + audit simulation | Siap audit basic
15.00–15.15 | Break
15.15–16.30 | Line Feeding & Production Continuity | - Feeding system- Supermarket | - OEM expectation: • Zero line stop • No material shortage • JIT support | Simulasi line stop | Paham dampak ke OEM
16.30–17.00 | Review Day 1 | - Recap + diskusi | - Gap vs OEM expectation | Diskusi | Awareness meningkat
HARI 2 — IMPLEMENTATION + OEM COMPLIANCE PRACTICE
Waktu | Modul | Materi Utama | Integrasi Perspektif OEM (Ford) | Metode | Output
08.30–09.00 | Review | - Quiz + recap | - Highlight risk ke OEM | Quiz | Recall
09.00–10.30 | Production Planning & MRP | - Forecast → MPS → MRP | - OEM demand: • Schedule stability • No last-minute change • Capacity alignment | Simulasi | Paham planning stabil
10.30–10.45 | Break
10.45–12.00 | Supplier Management (OEM Requirement) | - Supplier control - Delivery monitoring | - Ford requirement: • Supplier OTD ≥95% • ASN mandatory • Risk mitigation | Studi kasus | Paham inbound risk
12.00–13.00 | Lunch
13.00–14.15 | Export Logistics & OTIF | - Container planning - Export flow | - OEM demand: • OTIF ≥98% • No delay shipment • Accurate documentation | Simulasi export | Paham export criticality
14.15–15.15 | Traceability & Risk Control | - Batch tracking- Recall readiness | - Ford critical: • Full traceability (RM → tyre) • Recall < 24–48 jam • Data accuracy tinggi | Case study recall | Paham traceability
15.15–15.30 | Break
15.30–16.30 | MMOGLE Level A + OEM Audit Simulation | - Checklist Level A - Audit simulation | - Auditor fokus: • Data vs actual • FIFO • System reliability | Mock audit | Siap audit
16.30–17.15 | Integrated Case Study (Tyre OEM Scenario) | - Kasus: • Shipment delay • Wrong batch • Line stop | - Analisa dampak ke OEM: • Production shutdown • Claim cost • Supplier downgrade | Group discussion | Problem solving
17.15–17.30 | Closing & Post-Test | - Evaluasi | - Komitmen improvement | Quiz | Action plan